# GLOBAL OPERATIONS BRIEF

2026 INTERNATIONAL EDITION • BOARD READY

A practical view of performance across the Americas, Europe, Asia-Pacific, and Middle East & Africa — with multilingual content, tables, governance notes, and decision-ready recommendations.

| PERIOD | REPORTING SCOPE | STATUS |
| --- | --- | --- |
| FY 2026 H1 | 4 regions • 12 markets | ON TRACK |

# 1. Executive summary

Flyfish Group enters the second half of 2026 with resilient demand and improved delivery discipline. Regional revenue is 8.4% above plan while service availability remains at 99.97%. The priority now is to convert pipeline quality into predictable recurring growth without compromising customer experience.

- Protect enterprise renewal momentum in North America and Europe.

- Accelerate partner-led launches in Japan, Singapore, and the Gulf.

- Standardize multilingual onboarding, support, and reporting workflows.

# 2. Regional performance

| REGION | REVENUE | VS PLAN | RETENTION |
| --- | --- | --- | --- |
| Americas | $8.6M | +7.2% | 96.4% |
| Europe | $6.9M | +9.8% | 95.7% |
| Asia-Pacific | $5.4M | +11.6% | 94.9% |
| Middle East & Africa | $2.7M | +4.1% | 93.8% |

## Americas and Europe

Enterprise expansions led performance. The combined region added 21 strategic accounts and reduced onboarding time from 18 to 12 business days through reusable implementation blueprints.

## Asia-Pacific and MEA

Partner channels generated 43% of new pipeline. Localization quality and time-zone coverage remain the strongest predictors of successful activation, particularly for Japan and the Gulf markets.

# 3. Operating priorities

- Unify the customer launch playbook across sales, delivery, and support.

- Publish localized enablement packs for English, Chinese, Japanese, and Arabic audiences.

- Introduce weekly risk reviews with owners, due dates, and measurable exit criteria.

| RISK | EXPOSURE | OWNER | MITIGATION |
| --- | --- | --- | --- |
| Localization delay | Medium | Regional Ops | Pre-approved language packs |
| Capacity concentration | High | Platform | Multi-region failover drill |
| Partner readiness | Medium | Alliances | Certification sprint |
| Forecast variance | Low | Finance | Weekly pipeline hygiene |

# 4. Decision framework

Approve initiatives that meet all three tests: customer evidence, measurable operating leverage, and a clear 90-day owner. Defer projects that add local complexity without creating reusable capability.

# 5. Multilingual customer note

## English

Your documents remain under your control. Office Preview processes supported files in the browser and loads format-specific components only when needed.

## 简体中文

您的文档始终由您掌控。Office Preview 在浏览器中处理受支持的文件，并仅在需要时加载对应格式组件。

## 日本語

ドキュメントは常にお客様の管理下にあります。対応ファイルはブラウザー内で処理され、必要な形式のコンポーネントだけが読み込まれます。

## العربية

تظل مستنداتك تحت سيطرتك. تتم معالجة الملفات المدعومة داخل المتصفح، ولا يتم تحميل مكونات التنسيق إلا عند الحاجة.

# 6. Next 90 days

| MILESTONE | DATE | SUCCESS MEASURE |
| --- | --- | --- |
| Regional playbook v2 | 15 August | 100% launch coverage |
| Partner certification | 12 September | 30 certified partners |
| Localization baseline | 30 September | 4 production languages |
| Executive review | 10 October | Decision on FY 2027 scale plan |